## Team
Initials | First | Last | Email | GitHub Username
ykw | Yikan | Wang
lwk | Lingwen | Kong | lkong11@stevens.edu | konglingwengit
hyz | Hengyuan | Zhang | hzhan56@stevens.edu | hygithub3901
myl | Muyang | Li
|  |  | GitHub Repository: | https://github.com/konglingwengit/SSW-555-A-Project-3/

## Backlog
Sprint | Story ID | Story Name | Owner | Status
1 | US01 | Dates before current date | hyz | Done
1 | US02 | Birth before marriage | hyz | Coding
1 | US03 | Birth before death | myl | Coding
1 | US10 | Marriage after 14 | ykw | Coding
1 | US11 | No bigamy | ykw | Coding
1 | US06 | Divorce before death | myl | Coding
1 | US07 | Less then 150 years old | lwk | Done
1 | US29 | List deceased | lwk | Done

## Burndown
Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
2021-03-04

## Sprint1
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US01 | Dates before current date | hyz | Done | 100 | 60 | 90 | 70 | 2021-03-03 | Review Results
T01.01 | Store read file date | hyz | [6 empty] | Keep doing:
T01.02 | Store current date | hyz | [6 empty] | Add marriage date
T01.03 | Compare read date and current date | hyz
US02 | Birth before marriage | hyz | Coding | 100 | 60 |  |  |  | Avoid:
T02.01 | Store birth date | hyz | Done
T02.02 | Store marriage date | hyz
T02.03 | Compare birth date and marriage date | hyz
US07 | Less then 150 years old | lwk | done | 100 | 70 | 95 | 50 | 2021-03-03
T03.01 | Store birth date | lwk | done | 50 | 30 | 45 | 25 | 2021-03-03
T03.02 | Compare to current date | lwk | done | 50 | 40 | 50 | 25 | 2021-03-03
US29 | List deceased | lwk | done | 100 | 70 | 90 | 60 | 2021-03-03
T029.01 | Check DEAT status | lwk | done | 50 | 30 | 45 | 30 | 2021-03-03
T029.02 | Append object on list | lwk | done | 50 | 40 | 45 | 30 | 2021-03-03
US10 | Check marriage if before 14 | WYK | coding | 50 | 50
US11 | check if marry twice at same time | WYK | coding | 50 | 50